## Rajveer Singh
To-do list
To be completed by: |  | 2022-05-15 |  | Name: Rajveer Singh
Deadline: |  | 2022-05-15 |  | Date: 5/12
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-05-06 | 2022-05-06
100% | Writing Stored Procedures | 2022-05-09 | 2022-05-10
100% | Writing Queries | 2022-05-10 | 2022-05-11
100% | Creating Powerpoint Template | 2022-05-10 | 2022-05-10
100% | Queries for Analasys | 2022-05-12 | 2022-05-12
100% | Completeing Powerpoint | 2022-05-10 | 2022-05-11
100% | Powerpoint Video | 2022-05-11 | 2022-05-12
100% | JDBC Video | 2022-05-11 | 2022-05-12
100% | Finalization of Project | 2022-05-13 | 2022-05-13

## Eliyahu Roth
To-do list
To be completed by: |  | 2022-05-15 |  | Name Eliyahu Roth
Deadline: |  | 2022-05-15 |  | Date 5/12
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-05-06 | 2022-05-06
100% | Writing Stored Procedures | 2022-05-09 | 2022-05-10
100% | Writing Queries | 2022-05-10 | 2022-05-11
100% | Filling in PowerPoint | 2022-05-12 | 2022-05-12
100% | Modifying JDBC | 2022-05-13 | 2022-05-13
100% | Powerpoint Video | 2022-05-11 | 2022-05-12
100% | JDBC Video | 2022-05-11 | 2022-05-12
100%
100%

## Meet Patel
To-do list
To be completed by: |  | 2022-05-15 |  | Name: Meet Patel
Deadline: |  | 2022-05-15 |  | Date: 5/12
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-05-06 | 2022-05-06
100% | Database Cleansing | 2022-05-07 | 2022-05-08
100% | Database Normalization | 2022-05-07 | 2022-05-09
100% | Writing Stored Procedures | 2022-05-09 | 2022-05-10
100% | Debugging Databse | 2022-05-10 | 2022-05-11
100% | Filling in PowerPoint | 2022-05-12 | 2022-05-12
100% | Powerpoint Video | 2022-05-11 | 2022-05-12
100% | JDBC Video | 2022-05-11 | 2022-05-12
0%

## Mashiur Rahman
To-do list
To be completed by: |  | 2022-05-15 |  | Name: Mashiur Rahman
Deadline: |  | 2022-05-15 |  | Date: 5/12
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Writing Queries | 2022-05-10 | 2022-05-11
100% | Filling in PowerPoint | 2022-05-12 | 2022-05-12
100% | Powerpoint Video | 2022-05-12 | 2022-05-13
100% | JDBC Video | 2022-05-11 | 2022-05-12
100% | JDBC Video | 2022-05-11 | 2022-05-12
0%
0%
0%
0%

## Edison Enerio
To-do list
To be completed by: |  | 2022-04-12 |  | Name: Edison Enerio
Deadline: |  | 2022-04-13 |  | Date: 5/12
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-05-06 | 2022-05-06
100% | Database Cleansing | 2022-05-07 | 2022-05-08
100% | Database Normalization | 2022-05-07 | 2022-05-09
100% | Writing Stored Procedures | 2022-05-09 | 2022-05-10
100% | Writing Queries | 2022-05-10 | 2022-05-11
100% | Filling in PowerPoint | 2022-05-12 | 2022-05-12
100% | Powerpoint Video | 2022-05-11 | 2022-05-12
100% | JDBC Video | 2022-05-11 | 2022-05-12
0%